## MVP Roadmap
Sprint | Mobile App (Customer) | Admin Panel (Staff) | AI Integration | Screens & Fields
Phase 1 – Foundation & Onboarding (0–2M)
Sprint 1 | Registration, Login/Logout, Profile Mgmt | User Mgmt (View/Edit, Block/Unblock) | N/A | Mobile – Registration: Full Name (Text, required), Email (Text, required), Phone (Numeric, 10 digits, required), Password (Password, min 8 chars, required), Confirm Password (Password, must match, required), Register (Button). Mobile – OTP: OTP (Numeric, 6 digits, required), Verify (Button), Resend OTP (Button). Mobile – Login: Email/Phone (Text, required), Password (Password, required), Login (Button), Forgot Password (Link). Mobile – Profile Mgmt: Full Name (Editable), Email (Read-only), Phone (Read-only), KYC Upload (File Upload – PDF/JPEG, ≤10MB, optional), Save Changes (Button). Admin – User Mgmt Dashboard: Search (Text), User List (Table: Name, Email, Phone, Status, Actions), Action Buttons (View/Edit/Block/Unblock).
Sprint 2 | Registration Fee Payment, Policy Upload | View Uploaded Policies | OCR baseline prep | Mobile – Registration Fee Payment: Amount (Auto-filled), Payment Method (Dropdown: Card, UPI, NetBanking, Wallet), Pay Now (Button). Mobile – Policy Upload: Policy Type (Dropdown: Health/Life/Auto/Other, required), Policy Number (Text, alphanumeric, required), Insurer Name (Text), Start Date (Date picker), Expiry Date (Date picker), Upload Document (File Upload – PDF/JPEG/PNG ≤10MB, required), Submit (Button). Admin – Policy Mgmt: User ID (Text), Policy Type (Dropdown), Policy Number (Text), Status (Dropdown: Uploaded/Verified/Invalid), Action Buttons (Verify/Reject).
Phase 2 – Claims & Ticketing (2–4M)
Sprint 3 | Raise Claim Ticket, Ticket Status | Ticket Mgmt (Assign, Update, Escalate) | OCR parsing rejection docs, Auto-tag claim type | Mobile – Raise Claim: Select Policy (Dropdown – user’s uploaded policies), Upload Rejection Letter (File Upload – PDF/JPEG/PNG ≤10MB, required), Comments (Multiline Text, optional), Submit Ticket (Button). Mobile – Ticket Status: Ticket List (Table: Ticket ID, Policy Linked, Status, Last Updated), View Details (Button). Admin – Ticket Mgmt: Ticket List (Table: Ticket ID, User, Policy Number, Status, Assigned Agent, Actions), Assign Agent (Dropdown), Status (Dropdown: Pending/In Progress/Resolved/Escalated), Notes (Multiline Text), Update (Button).
Sprint 4 | Chat with Support, Notifications (SMS/Email) | Chat Panel for Tickets | Claim Classifier: Suggest rejection cause | Mobile – Chat Screen: Conversation Thread (List), Message Box (Text), Attachment Upload (File optional ≤5MB), Send (Button). Admin – Ticket Chat Panel: Ticket ID (Text), Conversation Thread (List), Reply Box (Text), Attachment Upload (File ≤5MB), Send (Button).
Phase 3 – Payments & Communication (4–6M)
Sprint 5 | Consultation Fee Payment | Payment Reports, Mark Paid/Unpaid, Invoice Gen. | Smart Reminder AI (auto reminders for pending payments/docs) | Mobile – Consultation Payment: Amount (Auto), Payment Method (Dropdown: Card/UPI/NetBanking/Wallet), Pay (Button). Admin – Payments Panel: Payment List (Table: User, Ticket ID, Fee Status), Fee Status (Dropdown: Paid/Unpaid), Export Report (Button), Generate Invoice (Button – PDF).
Sprint 6 | Push Notifications, FAQ Chatbot v1 | Dashboard (Tickets, Users, Payments summary) | FAQ Chatbot (trained on FAQs) | Mobile – Notifications Center: Notification List (Cards), Filter (Dropdown: Read/Unread), Mark as Read (Action). Mobile – FAQ Chatbot: Question (Text Input), Send (Button), AI Response (Dynamic Text). Admin – Dashboard: Stats (Cards: Total Users, Active Tickets, Payments), Graphs (Bar/Pie), Refresh (Button).
Phase 4 – Advanced AI & Assist (6–8M)
Sprint 7 | Draft Reconsideration Letters (Preview & Submit) | AI Assist Panel (Suggest Actions, Draft Letters, Case Matching) | GPT-based auto drafting, Case Pattern Matching AI | Mobile – Draft Letter Preview: Draft Text (Auto-generated), Accept (Button), Reject (Button). Admin – AI Assist Panel: Ticket ID (Text), Suggested Actions (Auto Text), Draft Letter (Auto Text Area), Approve Draft (Button), Reject Draft (Button).
Sprint 8 | Fraud/Suspicious Upload Alerts, Sentiment Alerts | Fraud Detection, Sentiment Dashboard, AI Feedback Loop | Fraud Detection AI (duplicate docs/profiles), Sentiment AI | Mobile – Fraud/Sentiment Alerts: Alert Message (Dynamic Text), Contact Support (Button). Admin – Fraud Detection Dashboard: Alerts (Table: User, Issue Type, Risk Score), Action (Review/Confirm). Admin – Sentiment Dashboard: Ticket ID (Text), Sentiment Score (Auto: Positive/Neutral/Negative), Urgency Flag (Toggle), Action (Escalate/Ignore).

## Post-MVP Backlog
Feature | Benefit
Predictive Approval Score | Suggest to users whether claim reconsideration is worth pursuing
AI-based Policy Comparison | Help customers compare similar policies when adding new ones
Analytics Dashboard (Advanced) | Agent productivity, most common rejection reasons, trends